## README
Audit ledger — example workbook
Built from workbook.md on 2026-09-13 with generic names. Sample data only: Project Alpha, Vendor A, Vendor B.
How to read the colours
Blue text on a yellow fill = data you paste or type. Black text = formulas; do not edit.
Sheets
Lines Every row from every Stage 1 CSV, pasted under the last row. Columns A–V are the CSV; W onward are helper formulas that must be filled down to the last row.
Mapping The label table. Paste this whole range into every Stage 1 chat. Add a row when Review shows 'no mapping rule'.
Docs One row per document, derived from the coverage rows. Stated totals vs extracted totals, sum checks, page coverage.
Tracker One row per project and vendor. Quoted vs invoiced by category, variance, discrepancy flag.
Detail Every line that differs between a quote and its invoices: quote only, invoice only, or amount differs.
Review Everything a human should look at. Empty means no PDF needs opening.
Notes Where Stage 3 output is pasted. Tracker and Detail look notes up from here.
Settings The tolerance for 'matches exactly', and the client's billing standards for Stage 3.
Adding a document
1. Open the CSV the model returned. 2. Copy its data rows (not the header). 3. Paste under the last row of Lines. 4. Fill the helper formulas (W onward) down to the new last row. Everything else updates.
Phase B: Data > Get Data > From Folder on csv/ loads Lines automatically; keep the helper columns beside the query table.
What the sample data shows
Vendor A: installation billed by the hour on top of the fixed price (invoice-only line), freight above quote (amount differs), contingency not drawn (quote only), one label no rule fits (UNMAPPED, in Review).
Vendor B: quote only, no invoice yet, so Tracker says pending. Scan with one unread page and a stated product total that does not match its lines: both in Review.
Compatibility note
workbook.md sketches Docs, Tracker, Detail and Review with FILTER, UNIQUE and VSTACK. This file uses the equivalent INDEX/MATCH helper-column pattern so it works in every Excel version and could be verified outside Excel. Same results, longer formulas.

## Settings
Setting | Value
Tolerance (amounts within this are 'matched exactly') | 0.01
Billing standards (paste into the Stage 3 chat)
1. Labour is billed at the quoted fixed rate unless a signed change order authorises time and materials.
2. Installation cost is itemised as a distinct line from product cost.
3. Product cost is invoiced consistent with the manufacturer-confirmed quote.
4. Allowance items require documented approval before being invoiced.

## Lines
row_kind | project | vendor | doc_type | doc_id | doc_date | ref_quote_id | page | line_no | label_as_printed | description | qty | unit_amount | amount | category | confidence | note | pages_total | pages_read | native_or_scan | mapping_provided | source_file | match_key | labour_group | invoice_amount | invoice_hits | quote_hits | status | detail_seq | review_reason | review_seq | coverage_seq | pair_seq
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 1 | 1 | Task chair TC-200 | Task chair, model TC-200 | 40 | 350 | 14000 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 1 | 2 | Desk HA-1600 | Height-adjustable desk 1600 | 40 | 620 | 24800 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 2 | 3 | Pedestal | Storage pedestal | 40 | 180 | 7200 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 2 | 4 | Installation | Installation, 40 workstations, fixed price |  |  | 9600 | INSTALL | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 2 | 5 | Project management | Project management fee |  |  | 2400 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 2 | 6 | Freight | Freight to site |  |  | 1800 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 | 7 | Contingency | Contingency allowance |  |  | 2000 | ALLOWANCE | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 | 8 | Sales tax | Sales tax 8% |  |  | 3680 | EXCLUDED | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
total | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 |  | Product subtotal |  |  |  | 46000 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
total | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 |  | Installation |  |  |  | 9600 | INSTALL | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
total | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 |  | Services subtotal |  |  |  | 4200 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
total | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 |  | 3 |  | Grand total |  |  |  | 65480 | GRAND | H | [5 empty] | Project Alpha__Vendor A__quote__Q-1001.pdf
coverage | Project Alpha | Vendor A | quote | Q-1001 | 2026-05-04 | [11 empty] | 3 | 1-3 | native | Y | Project Alpha__Vendor A__quote__Q-1001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 1 | 1 | Task chair TC-200 | Task chair, model TC-200 | 40 | 350 | 14000 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 1 | 2 | Desk HA-1600 | Height-adjustable desk 1600 | 40 | 620 | 24800 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 1 | 3 | Pedestal | Storage pedestal | 40 | 180 | 7200 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 4 | Installation | Installation, 40 workstations, fixed price |  |  | 9600 | INSTALL | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 5 | Install labour - additional hours | Additional installation hours, 32 hrs at 95 | 32 | 95 | 3040 | INSTALL | M | matched by principle |  |  |  |  | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 6 | Project management | Project management fee |  |  | 2400 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 7 | Freight | Freight to site |  |  | 2100 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 8 | Site services | Site services |  |  | 650 | UNMAPPED | L | no mapping rule |  |  |  |  | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 | 9 | Sales tax | Sales tax 8% |  |  | 3680 | EXCLUDED | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
total | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 |  | Product subtotal |  |  |  | 46000 | PRODUCT | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
total | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 |  | Installation |  |  |  | 12640 | INSTALL | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
total | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 |  | Services subtotal |  |  |  | 4500 | LABOUR | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
total | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | 2 |  | Grand total |  |  |  | 67470 | GRAND | H | [5 empty] | Project Alpha__Vendor A__invoice__INV-2001.pdf
coverage | Project Alpha | Vendor A | invoice | INV-2001 | 2026-07-15 | Q-1001 | [10 empty] | 2 | 1-2 | native | Y | Project Alpha__Vendor A__invoice__INV-2001.pdf
line | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 1 | 1 | Meeting table MT-3200 | Meeting table 3200 | 4 | 2900 | 11600 | PRODUCT | H | [5 empty] | Project Alpha__Vendor B__quote__Q-1002.pdf
line | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 2 | 2 | Conference chair | Conference chair | 32 | 410 | 13120 | PRODUCT | M | scan, figure clear |  |  |  |  | Project Alpha__Vendor B__quote__Q-1002.pdf
line | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 2 | 3 | Credenza | Credenza | 4 | 1450 | 5800 | PRODUCT | L | figure partly legible |  |  |  |  | Project Alpha__Vendor B__quote__Q-1002.pdf
line | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 3 | 4 | Labour | Delivery and installation |  |  | 4200 | INSTALL | M | matched by principle |  |  |  |  | Project Alpha__Vendor B__quote__Q-1002.pdf
total | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 4 |  | Product subtotal |  |  |  | 30620 | PRODUCT | H | [5 empty] | Project Alpha__Vendor B__quote__Q-1002.pdf
total | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 |  | 4 |  | Grand total |  |  |  | 34820 | GRAND | H | [5 empty] | Project Alpha__Vendor B__quote__Q-1002.pdf
coverage | Project Alpha | Vendor B | quote | Q-1002 | 2026-05-10 | [10 empty] | page 5 illegible | 5 | 1-4 | scan | Y | Project Alpha__Vendor B__quote__Q-1002.pdf

## Mapping
label_as_printed | category | vendor | note
Installation | INSTALL | any
Install labour | INSTALL | any
Delivery & install | INSTALL | any
Labour | INSTALL | any | Confirm per vendor; some print labour for design time
Design fee | LABOUR | any
Project management | LABOUR | any
Freight | LABOUR | any
Allowance | ALLOWANCE | any
Contingency | ALLOWANCE | any
Sales tax | EXCLUDED | any
Surcharge | EXCLUDED | any

## Notes
tracker_notes (paste Stage 3 output here; column E is a formula)
project | vendor | category | note | key
Project Alpha | Vendor A | LABOUR_ALL | Invoiced above quoted. See Detail: 2 lines, additional installation hours and a higher freight charge.
Project Alpha | Vendor A | INSTALL | Invoiced above quoted. See Detail: 1 invoice-only line, installation hours billed by the hour.
Project Alpha | Vendor A | PRODUCT | matched exactly
Project Alpha | Vendor A | ALLOWANCE | Invoiced below quoted. See Detail: 1 quote-only line, contingency not drawn.
detail_notes (paste Stage 3 output here; column G is a formula)
project | vendor | doc_id | line_no | standard_ref | note | key
Project Alpha | Vendor A | INV-2001 | 5 | 1 | Hourly installation labour billed on top of the fixed-price installation line.
Project Alpha | Vendor A | Q-1001 | 6 | NONE | Freight invoiced above the quoted amount.

## Docs
seq | row | doc_id | project | vendor | doc_type | doc_date | pages_total | pages_read | native_or_scan | mapping_provided | source_file | stated_LABOUR_ALL | extracted_LABOUR_ALL | check_LABOUR_ALL | stated_INSTALL | extracted_INSTALL | check_INSTALL | stated_PRODUCT | extracted_PRODUCT | check_PRODUCT | stated_ALLOWANCE | extracted_ALLOWANCE | check_ALLOWANCE | stated_GRAND | extracted_ALL | check_GRAND | dup_count | review_reason | review_seq
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Tracker
seq | row | project | vendor | quoted_LABOUR_ALL | invoiced_LABOUR_ALL | variance_LABOUR_ALL | variance_pct_LABOUR_ALL | quoted_INSTALL | invoiced_INSTALL | variance_INSTALL | variance_pct_INSTALL | quoted_PRODUCT | invoiced_PRODUCT | variance_PRODUCT | variance_pct_PRODUCT | quoted_ALLOWANCE | invoiced_ALLOWANCE | variance_ALLOWANCE | variance_pct_ALLOWANCE | invoice_count | discrepancy | notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Detail
seq | row | project | vendor | doc_type | doc_id | ref_quote_id | page | line_no | label_as_printed | description | category | quote_amount | invoice_amount | variance | status | note
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Review
seq | doc_id | page | line_no | label_as_printed | reason
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100